Goals
8 weeks at a time

- December 6 – December 31
  - Set up Wiki
  - Set up Forum
  - Set up IRC
  - Set up Webinar plan
  - Set up email lists and auto archive manager (scale inspired)
  - Develop a weekly email template
  - Develop a Social media plan with repeatable actions as foundation
  - Develop an elevator pith (add this to what to learn/come up with for new members)
  - Develop Quick Start plan
  - Finish presentation to for Scale / tour
  - Set up a “tasks” board (maybe a ticket system?)
  - Evolve Application Document to give a better picture of the goal of the platform
  - Develop Information Party elected representative Document
  - Put together a soft “launch” of the party. Contacting all email list and original founders
  - Update website with the evolved ideals and purpose of the party
- January 1 – February 25
  - Set the party up as a single proper legal entity
    - Cost?
    - Type?
    - Why?
  - Collect enough signatures in each state to register as a political party
    - How many required for each state
    - Any additional special requirements in each state
- February 26 – April 22
- April 23 – June 17
- June 18 – August 19
- August 20 – October 14
- October 15 – November Elections